## Legend
CareSaath — Dev Tracker
Source | CareSaath SRS (Sep 23, 2026). Tasks are derived from SRS requirements; nothing is invented. Unknowns are marked TBD (see Open Questions sheet).
Companion docs | CARESAATH_ERD.md, CARESAATH_TRD.md
Sheets | Summary (auto-counts) · Backend · Frontend · Open Questions
Cells you edit | Owner, Status, Start, Due, Notes (blue text). Status uses a dropdown. Everything else is pre-filled from the SRS.
Status values | Not Started · In Progress · In Review · Blocked · Done
Priority | High = needed for a working MVP flow or required by SRS constraints. Medium/Low = can follow. Priority is a proposal; adjust freely.
Phases | P0 Setup · P1 Core (auth, onboarding, verification) · P2 Booking & Visits · P3 Payments · P4 Safety & Admin · P5 Hardening
Estimates / dates | Not filled in. Effort estimates need team size and decisions in Open Questions (TBD).
Frontend note | Customer-app framework and caregiver panel (web vs native) are undecided in the SRS; see Open Questions #1 and #2.

## Summary
Progress Summary
Status | Backend | Frontend | Total
Not Started | 67 | 48 | 115
In Progress | 0 | 0 | 0
In Review | 0 | 0 | 0
Blocked | 0 | 0 | 0
Done | 0 | 0 | 0
Total tasks | 67 | 48 | 115
% Done | 0% | 0% | 0%
Tasks by phase
Phase | Total | Done | % Done
P0 Setup | 12 | 0 | 0%
P1 Core | 24 | 0 | 0%
P2 Booking & Visits | 31 | 0 | 0%
P3 Payments | 15 | 0 | 0%
P4 Safety & Admin | 20 | 0 | 0%
P5 Hardening | 13 | 0 | 0%
Open questions still unresolved | 31

## Backend
ID | Module | Task | SRS Ref | Phase | Priority | Owner | Status | Start | Due | Notes
BE-001 | Setup | Initialise NestJS + TypeScript project, npm scripts, lint/format | TRD §3.3 | P0 Setup | High |  | Not Started
BE-002 | Setup | Docker Compose: postgres, redis, minio, mailhog, backend | TRD §10.1 | P0 Setup | High |  | Not Started |  |  | Version pins TBD
BE-003 | Setup | Prisma setup, initial schema from ERD, migrations, seed script | ERD | P0 Setup | High |  | Not Started
BE-004 | Setup | Config module + .env validation; tunable-values table | TRD §4 | P0 Setup | High |  | Not Started |  |  | Holds TBD windows/limits
BE-005 | Setup | Global validation, exception filter, logging, pagination, Swagger | TRD §5 | P0 Setup | Medium |  | Not Started
BE-006 | Setup | MinIO service wrapper (upload, pre-signed URL, bucket policy) | TRD §7 | P0 Setup | High |  | Not Started
BE-007 | Setup | CI pipeline (install, lint, type-check, test, build) | TRD §10.4 | P0 Setup | Medium |  | Not Started |  |  | CI tool TBD
BE-008 | Auth | OTP request endpoint (generate, hash, store in Redis, send SMS) | FR-C1 | P1 Core | High |  | Not Started |  |  | SMS vendor TBD
BE-009 | Auth | OTP verify endpoint, issue JWT access + refresh | FR-C1 | P1 Core | High |  | Not Started |  |  | TTLs TBD
BE-010 | Auth | Refresh/logout, token deny-list in Redis | TRD §5.1 | P1 Core | Medium |  | Not Started
BE-011 | Auth | Role guards (Customer/Caregiver/Admin) + ownership checks | SRS §2.3 | P1 Core | High |  | Not Started
BE-012 | Auth | OTP/login rate limiting | TRD §7 | P1 Core | High |  | Not Started |  |  | Limits TBD
BE-013 | Auth | Admin login method | SRS §8.1 | P1 Core | Medium |  | Not Started |  |  | TBD: SRS silent
BE-014 | Users | User CRUD, language preference (EN/UR), status handling | SRS §2.5 | P1 Core | Medium |  | Not Started
BE-015 | Patients | Patient profile CRUD (self / family member, medical context) | FR-C2 | P1 Core | High |  | Not Started |  |  | Fields TBD; encrypt
BE-016 | Addresses | Address CRUD with lat/lng | FR-C7 | P1 Core | High |  | Not Started
BE-017 | Caregiver | Caregiver registration (name, CNIC, license no.) | FR-CG1 | P1 Core | High |  | Not Started |  |  | Encrypt CNIC
BE-018 | Caregiver | Certificate/license document upload to MinIO | FR-CG1 | P1 Core | High |  | Not Started
BE-019 | Caregiver | Profile: specialty, service area, rate per visit | FR-CG3 | P1 Core | High |  | Not Started |  |  | Service-area model TBD
BE-020 | Caregiver | Public caregiver profile endpoint (quals, license no., experience, ratings, rate) | FR-C4 | P1 Core | High |  | Not Started
BE-021 | Verification | Admin queue + approve/reject endpoints, block unapproved from search | FR-CG2, FR-A1 | P1 Core | High |  | Not Started |  |  | No unverified profile goes live
BE-022 | Verification | Periodic re-verification due dates + reminders | FR-A2 | P4 Safety & Admin | Medium |  | Not Started |  |  | Interval TBD (annual example)
BE-023 | Availability | Weekly availability rules CRUD | FR-CG4 | P2 Booking & Visits | High |  | Not Started
BE-024 | Availability | Blocked dates CRUD | FR-CG4 | P2 Booking & Visits | High |  | Not Started
BE-025 | Search | Caregiver search by specialty, location, availability | FR-C3 | P2 Booking & Visits | High |  | Not Started
BE-026 | Search | DB indexes + Redis caching to meet <3s on 3G | SRS §6 | P2 Booking & Visits | High |  | Not Started |  |  | Target definition TBD
BE-027 | Booking | Create single booking (date, time window, address, patient) | FR-C6, FR-C7 | P2 Booking & Visits | High |  | Not Started
BE-028 | Booking | Recurring booking: generate one visit per occurrence | FR-C6 | P2 Booking & Visits | High |  | Not Started |  |  | Allowed patterns TBD
BE-029 | Booking | Double-booking prevention (transactional availability check) | FR-CG4 | P2 Booking & Visits | High |  | Not Started |  |  | Design
BE-030 | Booking | Prescription/care-plan upload with booking | FR-C5 | P2 Booking & Visits | High |  | Not Started |  |  | File rules TBD
BE-031 | Booking | Caregiver accept/decline within response window | FR-CG5 | P2 Booking & Visits | High |  | Not Started |  |  | Window + timeout behaviour TBD
BE-032 | Booking | Customer cancel/reschedule within notice window | FR-C13 | P2 Booking & Visits | High |  | Not Started |  |  | Window TBD; Cancelled state is a gap-fill
BE-033 | Visits | Visit state machine (Requested → … → Completed) + history table | FR-C9, SRS §8.2 | P2 Booking & Visits | High |  | Not Started
BE-034 | Visits | En-route endpoint | FR-C9 | P2 Booking & Visits | Medium |  | Not Started |  |  | Trigger (manual vs auto) TBD
BE-035 | Visits | Check-in/check-out via GPS or OTP, store coordinates | FR-CG7 | P2 Booking & Visits | High |  | Not Started |  |  | GPS radius TBD
BE-036 | Visits | Visit note submit (moves to Completed) + customer view | FR-CG8, FR-C11 | P2 Booking & Visits | High |  | Not Started
BE-037 | Visits | Caregiver view of patient context + prescription (secured access) | FR-CG6 | P2 Booking & Visits | High |  | Not Started |  |  | Only assigned caregiver + admin
BE-038 | Notifications | Notification service + event triggers on status change | FR-C10 | P2 Booking & Visits | High |  | Not Started
BE-039 | Notifications | SMS integration | FR-C10, SRS §7.3 | P2 Booking & Visits | High |  | Not Started |  |  | Vendor TBD
BE-040 | Notifications | WhatsApp Business API integration + templates | FR-C10, SRS §7.3 | P3 Payments | Medium |  | Not Started |  |  | Provider/approval TBD
BE-041 | Notifications | Push notification integration | FR-C10 | P3 Payments | Medium |  | Not Started |  |  | Provider TBD
BE-042 | Reviews | Rating + review after completed visit; update caregiver rating | FR-C12 | P3 Payments | Medium |  | Not Started |  |  | Scale TBD
BE-043 | Payments | Payment records + cash-on-visit flow | FR-C8 | P3 Payments | High |  | Not Started |  |  | Cash settlement TBD
BE-044 | Payments | JazzCash integration + signed idempotent webhook | FR-C8, SRS §7.2 | P3 Payments | High |  | Not Started |  |  | Merchant docs needed
BE-045 | Payments | Easypaisa integration + webhook | FR-C8, SRS §7.2 | P3 Payments | High |  | Not Started |  |  | Merchant docs needed
BE-046 | Payments | Card gateway integration + webhook | FR-C8, SRS §7.2 | P3 Payments | High |  | Not Started |  |  | Vendor TBD
BE-047 | Payments | Raast integration | SRS §7.2 | P3 Payments | Low |  | Not Started |  |  | Usage TBD
BE-048 | Commissions | Commission rate config per category + calculation at payment | FR-A4 | P3 Payments | High |  | Not Started |  |  | Rates TBD
BE-049 | Payouts | Earnings summary endpoint | FR-CG9 | P3 Payments | Medium |  | Not Started
BE-050 | Payouts | Payout account + payout request to bank/wallet | FR-CG9 | P3 Payments | Medium |  | Not Started |  |  | Approval flow TBD; encrypt accounts
BE-051 | Promos | Promo code CRUD + apply at booking | FR-A8 | P4 Safety & Admin | Low |  | Not Started |  |  | Platform-wide discount scope TBD
BE-052 | Safety | Safety complaint tied to visit (customer) | FR-C14 | P4 Safety & Admin | High |  | Not Started
BE-053 | Safety | Caregiver safety/access report | FR-CG10 | P4 Safety & Admin | High |  | Not Started
BE-054 | Safety | SOS endpoint: alert admin + emergency contact | SRS §9.2 | P4 Safety & Admin | High |  | Not Started |  |  | Recipient TBD
BE-055 | Safety | Incident management: priority escalation + audit trail | FR-A6 | P4 Safety & Admin | High |  | Not Started |  |  | Priority levels TBD
BE-056 | Disputes | Dispute create/mediate/resolve endpoints | FR-A7 | P4 Safety & Admin | Medium |  | Not Started |  |  | Workflow TBD
BE-057 | Admin | Suspend/deactivate caregiver | FR-A3 | P4 Safety & Admin | High |  | Not Started
BE-058 | Admin | Analytics endpoint (bookings, revenue, active caregivers, cancellation rate) | FR-A5 | P4 Safety & Admin | Medium |  | Not Started
BE-059 | Admin | CSV/Excel export of financial and operational reports | FR-A9 | P4 Safety & Admin | Medium |  | Not Started
BE-060 | Audit | Audit log service (credential approvals, check-in/out, incidents) | SRS §6 | P1 Core | High |  | Not Started |  |  | Wire in as modules are built
BE-061 | Security | Field-level encryption (CNIC, medical context, payout accounts) | SRS §6 | P5 Hardening | High |  | Not Started |  |  | Key management TBD
BE-062 | Security | TLS + at-rest encryption config for Postgres/MinIO | SRS §6 | P5 Hardening | High |  | Not Started |  |  | Hosting TBD
BE-063 | Quality | Unit tests: state machine, commission, availability, OTP | TRD §11 | P5 Hardening | High |  | Not Started
BE-064 | Quality | E2E tests: login, booking→completion, webhooks, doc access control | TRD §11 | P5 Hardening | High |  | Not Started
BE-065 | Quality | Search performance test under throttled 3G | SRS §6 | P5 Hardening | Medium |  | Not Started
BE-066 | Quality | Idempotency/retry handling for booking, payment, check-in | SRS §6 | P5 Hardening | High |  | Not Started |  |  | No data loss on drop
BE-067 | Ops | Backups, health checks, monitoring for 99.5% uptime | SRS §6 | P5 Hardening | Medium |  | Not Started |  |  | Hosting TBD

## Frontend
ID | Module | Task | SRS Ref | Phase | Priority | Surface | Owner | Status | Start | Due | Notes
FE-001 | Setup | Next.js + TypeScript project, lint, folder structure | TRD §3.3 | P0 Setup | High | Admin / Caregiver (Next.js) |  | Not Started |  |  | Admin + caregiver (if web)
FE-002 | Setup | Customer app framework decision and project setup | SRS §7.1 | P0 Setup | High | Customer |  | Not Started |  |  | TBD: native vs other
FE-003 | Setup | i18n setup (English/Urdu) with RTL support | SRS §2.5, §6 | P0 Setup | High | Shared |  | Not Started
FE-004 | Setup | Typed API client from OpenAPI + auth/token handling | TRD §9 | P0 Setup | High | Shared |  | Not Started
FE-005 | Setup | Design system: tokens, components, large-text mode | SRS §7.1 | P0 Setup | Medium | Shared |  | Not Started
FE-006 | Shared | Language switcher in settings | SRS §6 | P1 Core | Medium | Shared |  | Not Started
FE-007 | Customer | Phone + OTP login screens | FR-C1 | P1 Core | High | Customer |  | Not Started
FE-008 | Customer | Patient profile create/edit (self or family) | FR-C2 | P1 Core | High | Customer |  | Not Started |  |  | Fields TBD
FE-009 | Customer | Saved addresses + map pin picker | FR-C7 | P1 Core | High | Customer |  | Not Started |  |  | Maps provider TBD
FE-010 | Customer | Caregiver search + filters (specialty, location, availability) | FR-C3 | P2 Booking & Visits | High | Customer |  | Not Started
FE-011 | Customer | Caregiver profile screen (quals, license no., experience, ratings, rate) | FR-C4 | P2 Booking & Visits | High | Customer |  | Not Started
FE-012 | Customer | Booking flow: single or recurring, date, time window, address | FR-C6, FR-C7 | P2 Booking & Visits | High | Customer |  | Not Started
FE-013 | Customer | Prescription/care-plan upload in booking | FR-C5 | P2 Booking & Visits | High | Customer |  | Not Started
FE-014 | Customer | Visit status tracking screen | FR-C9 | P2 Booking & Visits | High | Customer |  | Not Started
FE-015 | Customer | Caregiver identity + photo shown before visit | SRS §9.2 | P2 Booking & Visits | High | Customer |  | Not Started
FE-016 | Customer | Cancel/reschedule UI | FR-C13 | P2 Booking & Visits | High | Customer |  | Not Started |  |  | Window TBD
FE-017 | Customer | View caregiver visit notes | FR-C11 | P2 Booking & Visits | Medium | Customer |  | Not Started
FE-018 | Customer | Push/notification handling | FR-C10 | P2 Booking & Visits | Medium | Customer |  | Not Started
FE-019 | Customer | Payment screens (cash, card, JazzCash, Easypaisa) | FR-C8 | P3 Payments | High | Customer |  | Not Started
FE-020 | Customer | Rating and review screen | FR-C12 | P3 Payments | Medium | Customer |  | Not Started
FE-021 | Customer | Safety complaint form tied to a visit | FR-C14 | P4 Safety & Admin | High | Customer |  | Not Started
FE-022 | Customer | SOS button during active visit | SRS §9.2 | P4 Safety & Admin | High | Customer |  | Not Started
FE-023 | Customer | Large-text / simple-navigation option | SRS §7.1 | P5 Hardening | Medium | Customer |  | Not Started
FE-024 | Caregiver | Registration form (name, CNIC, license, certificate upload) | FR-CG1 | P1 Core | High | Caregiver |  | Not Started
FE-025 | Caregiver | Verification status screen (pending/approved/rejected) | FR-CG2 | P1 Core | High | Caregiver |  | Not Started
FE-026 | Caregiver | Profile: specialty, service area, rate | FR-CG3 | P1 Core | High | Caregiver |  | Not Started
FE-027 | Caregiver | Weekly availability + blocked dates | FR-CG4 | P2 Booking & Visits | High | Caregiver |  | Not Started
FE-028 | Caregiver | Incoming requests list with accept/decline + countdown | FR-CG5 | P2 Booking & Visits | High | Caregiver |  | Not Started
FE-029 | Caregiver | Visit detail: patient context + prescription viewer | FR-CG6 | P2 Booking & Visits | High | Caregiver |  | Not Started
FE-030 | Caregiver | En-route / check-in / check-out (GPS or OTP) | FR-CG7 | P2 Booking & Visits | High | Caregiver |  | Not Started
FE-031 | Caregiver | Visit note form | FR-CG8 | P2 Booking & Visits | High | Caregiver |  | Not Started
FE-032 | Caregiver | Earnings view + payout request + payout account | FR-CG9 | P3 Payments | Medium | Caregiver |  | Not Started
FE-033 | Caregiver | Safety/access issue report | FR-CG10 | P4 Safety & Admin | High | Caregiver |  | Not Started
FE-034 | Admin | Admin login + layout/navigation | SRS §7.1 | P1 Core | High | Admin |  | Not Started |  |  | Login method TBD
FE-035 | Admin | Caregiver verification queue: view documents, approve/reject | FR-A1 | P1 Core | High | Admin |  | Not Started
FE-036 | Admin | Suspend/deactivate caregiver | FR-A3 | P4 Safety & Admin | High | Admin |  | Not Started
FE-037 | Admin | Re-verification list/reminders | FR-A2 | P4 Safety & Admin | Medium | Admin |  | Not Started
FE-038 | Admin | Commission rate settings | FR-A4 | P3 Payments | High | Admin |  | Not Started
FE-039 | Admin | Safety incident console with priority and audit trail | FR-A6 | P4 Safety & Admin | High | Admin |  | Not Started
FE-040 | Admin | Dispute mediation screens | FR-A7 | P4 Safety & Admin | Medium | Admin |  | Not Started
FE-041 | Admin | Promo code management | FR-A8 | P4 Safety & Admin | Low | Admin |  | Not Started
FE-042 | Admin | Analytics dashboard | FR-A5 | P4 Safety & Admin | Medium | Admin |  | Not Started
FE-043 | Admin | Report export (CSV/Excel) | FR-A9 | P4 Safety & Admin | Medium | Admin |  | Not Started
FE-044 | Quality | Responsive checks: Chrome, Edge, Safari | SRS §7.6 | P5 Hardening | Medium | Shared |  | Not Started
FE-045 | Quality | Android 8+ / iOS 13+ device checks | SRS §7.6 | P5 Hardening | Medium | Customer |  | Not Started
FE-046 | Quality | Urdu/English UI review | SRS §6 | P5 Hardening | Medium | Shared |  | Not Started
FE-047 | Quality | Usability test: first-time / elderly-assisting user in 2 minutes | SRS §6 | P5 Hardening | Medium | Shared |  | Not Started
FE-048 | Quality | Offline/network-drop handling for check-in, notes, booking | SRS §6 | P5 Hardening | Medium | Shared |  | Not Started |  |  | Behaviour TBD

## Open Questions
# | Open question (TBD) | Affects | Suggested decider | Decision | Status
1 | Caregiver panel: web (SRS §2.4) or native app (SRS §7.1)? | Frontend scope, staffing | Product |  | Open
2 | Mobile framework for customer app (stack has Next.js only) | Customer app delivery | Tech lead |  | Open
3 | Pilot cities (1–2) and service-area model | Search design, seeding | Product |  | Open
4 | Fields inside 'basic medical context' (FR-C2) | Patient table, forms | Product / Compliance |  | Open
5 | Specialty list: elderly care and attendant appear in some places only | Enums, search filters | Product |  | Open
6 | Cancellation/reschedule notice window (FR-C13) | Rules, UI | Product |  | Open
7 | Caregiver response window and timeout behaviour (FR-CG5) | Booking flow | Product |  | Open
8 | Cancelled state missing from SRS §8.2 lifecycle | State machine | Product |  | Open
9 | Who triggers 'En Route' (caregiver or automatic) | Visit flow | Product |  | Open
10 | GPS radius / OTP flow for check-in | Check-in rules | Product |  | Open
11 | Payment per visit vs per booking; refund rules | Payments schema | Product / Finance |  | Open
12 | Cash-on-visit commission settlement | Finance design | Finance |  | Open
13 | Raast usage (payments, payouts, or both) | Payment integration | Finance |  | Open
14 | Commission percentages per category | Config | Business |  | Open
15 | Payout approval flow and timing | Payouts | Finance |  | Open
16 | Gateway merchant docs and credentials (JazzCash, Easypaisa, card) | Payment work blocked | Business |  | Open
17 | SMS, WhatsApp, push providers | Notifications | Tech lead |  | Open
18 | Maps provider | Address pin, search | Tech lead |  | Open
19 | Whose emergency contact receives SOS alert | Safety flow | Product / Compliance |  | Open
20 | Incident priority levels and escalation SLAs | Safety flow | Product |  | Open
21 | Dispute workflow and who may raise one | Disputes | Product |  | Open
22 | Admin login method | Auth | Tech lead |  | Open
23 | OTP expiry, max attempts, rate limits; JWT lifetimes | Auth | Tech lead |  | Open
24 | PNC/PMDC cross-check: manual or semi-automated; physio body name | Verification | Compliance |  | Open
25 | Re-verification interval (SRS example: annual) | Verification | Compliance |  | Open
26 | Data protection obligations, retention period, key management | Security | Compliance |  | Open
27 | Hosting provider, CI tool, monitoring | Infra, uptime | Tech lead |  | Open
28 | SRS §8.1 shows caregiver viewing analytics but FR-A5 is admin only | Scope | Product |  | Open
29 | Rating scale and review moderation | Reviews | Product |  | Open
30 | Recurring-schedule patterns allowed | Booking | Product |  | Open
31 | Promo code types; platform-wide discount scope | Promos | Business |  | Open